## Mobile Application_CMS
Revision History | Author |  |  | Description
19-03-2012 | OpenXcell Technolabs |  |  | Initial draft by OpenXcell Technolabs
"IAM - live" Application (LJMedia) for iPhone & Android
Task List |  | iPhone Timeline Estimation | Android Timeline Estimation | Notes
Project Initiation: Strategy & Research |  |  |  |  | For iPhone
Scope |  |  |  |  | Milestones | Amount
Project Kick-off meeting |  |  |  |  | Upfront | 1636
Determine project scope |  |  |  |  | Navigational Flow and Design Implementation | 1636
Project Management (Ongoing)
Define preliminary resources |  |  |  |  | Application development Phase I | 1636
Communication & management of development team |  |  |  |  | Application development Phase II | 1636
Analysis of Software Requirements |  |  |  |  | Application development Phase III & Testing & Deployment | 1636
Task List
Obtain Approval to proceed |  |  |  |  | Total | 8180
Review Software Specifications with team
Navigational Flow & Design Implementation |  | 10 -11 days | 10-11 days
Video Demo |  |  |  |  | For Android
Design Implementations |  |  |  |  | Milestones | Amount
Design Implementations based on the approved video |  |  |  |  | Upfront | 1636
Application Development |  |  |  |  | Navigational Flow and Design Implementation | 1636
Phase I |  | 16-17 days | 16-17 days
Profile Settings |  |  |  |  | Application development Phase I | 1636
Select profile as per the requirement, One profile needs to be on at least |  |  |  |  | Application development Phase II | 1636
5 groups: family, fiends, spare time, job, tempo |  |  |  |  | Application development Phase III & Testing & Deployment | 1636
Delete profile & Group Members
Selectable social networks: Facebook, Google+, LinkedIn, Twitter |  |  |  |  | Total | 8180
Profile view |  |  |  | The standard social network profile is shown, depending on the user privacy settings.
First Start of Program (Menu)
Terms & Conditions
Profile Menu |  |  |  | If there is no profile entered
Main Menu |  |  |  | If there is already a profile entered
Map |  |  |  | If the tracking already started and the app is reopened
Phase II |  | 16-17 days | 16-17 days
The GPS-Funktion (Background)
Offline Memory for 24h total.
Tracking rate depends on user speed.
Background Tracking when the app is already opened but not shown
OPTIONS (options menu)
Link to the general terms and conditions
GPS options: auto/high accuracy/battery saver
Privacy settings: High(standard)/medium/low
24h Route is shown for friends
Enter Promotion code
Link to FAQs -->Website |  |  |  | Website is out of scope
Ranking Function
Database collects position Data for longterm
Ranking for all users
Promo Function
Free Pro version if three friends are promoted
Advertising
Google Ads & iAds
Map View
Display Targets
Display Own Position
Menu in Upper Part of the Display
Advertising
24h routing for Group Members
View Member Profile
Filter Search
Display Multiple Targets to one target if too many persons are at one place (within 30m)
Phase III |  | 16-17 days | 16-17 days
Camera View
Targets
Radar
Advertising
Automatic map mode if in vertical Position |  |  |  | If turned horizontal the camera mode will show up
Testing & Deployment
QA Testing
Review Modular Code
Test Component Modules to Application Specifications
Identify anomalies to Application Specifications
Modify Code
Re-Test Modified Code
Apple Approval |  | Additional 7-10 days | N/A
OpenXcell Technolabs will work with Client and Apple to setup account, getting code approval and launching app on iTunes Marketplace
Note: |  |  |  | CMS development will work in parallel with the application.
Database Implementation |  |  |  | It will include Admin front-end pages and back-end web-services development.
Identify modular/tiered design parameters
Web-Services
Approval & Changes Process